## project
Task | Start | Sprint 1 | Sprint 2 | Sprint 3
Code the homepage | 1 |  | 1
Code the login/about page | 2 |  |  | 2
Code the bus page | 1 |  | 1
Code the genre page | 1 |  | 1
Code the price page | 1 |  | 1
Set up a database | 3 | 2 | 1
Actual Remaining Effort | 9 | 7 | 2 | 0
Estimated Remaining Effort | 9 | 6 | 3 | 0

## Sprint 1
Task | Start | Sprint 1 | Sprint 2 | Sprint 3
Code the homepage | 1
Code the login/about page | 2
Code the bus page | 1
Code the genre page | 1
Code the price page | 1
Set up a database | 3 | 2
Actual Remaining Effort | 9 | 7
Estimated Remaining Effort | 9 | 6 | 3 | 0
sprint 1
task | time
Establish "bus" database | 2 hours
Establish "type" database | 1 hour

## Sprint 2
Task | Start | Sprint 1 | Sprint 2 | Sprint 3
Code the homepage | 1 |  | 1
Code the login/about page | 2
Code the bus page | 1 |  | 1
Code the genre page | 1 |  | 1
Code the price page | 1 |  | 1
Set up a database | 3 | 2 | 1
Actual Remaining Effort | 9 | 7 | 2
Estimated Remaining Effort | 9 | 6 | 3 | 0
sprint 2
task | time
Establish "price" database | 2 hours
Code the price page | 1 hour
Code the bus page | 1 hour
Code the type page | 1 hour
Code the homepage | 30 minutes
Test | 10 minutes

## Sprint 3
Task | Start | Sprint 1 | Sprint 2 | Sprint 3
Code the homepage | 1 |  | 1
Code the login/about page | 2 |  |  | 2
Code the bus page | 1 |  | 1
Code the genre page | 1 |  | 1
Code the price page | 1 |  | 1
Set up a database | 3 | 2 | 1
Actual Remaining Effort | 9 | 7 | 2 | 0
Estimated Remaining Effort | 9 | 6 | 3 | 0
sprint 2
task | time
Code the login page | 30 minutes
Code the about page | 30 minutes
Test | 10 minutes